## Sheet1
Gantt Chart for "Travel app" project
Number | Task | Start Date | End Date | Duration | December/January/February
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Choosing the project | 2024-01-12 | 2024-03-12 | 3 | bar: December/January/February 1 to December/January/February 3
2 | Understanding the project | 2024-04-12 | 2024-06-12 | 3 | bar: December/January/February 4 to December/January/February 6
3 | Submission of project proposal | 2024-07-12 | 2024-07-12 | 1 | bar: December/January/February 7
4 | Software research | 2024-08-12 | 2024-12-12 | 5 | bar: December/January/February 8 to December/January/February 12
5 | Requirement analysis report | 13/12/2024 | 17/12/2024 | 5 | bar: December/January/February 13 to December/January/February 17
6 | ER-Diagram added | 15/01/2025 | 20/01/1025 | 5 | bar: December/January/February 18 to December/January/February 21
7 | Normalization Update & Submit | 2025-01-02 | 2025-07-02 | 7 | bar: December/January/February 22 to December/January/February 26
8 | Architectural Design Submit | 2025-08-02 | 2025-10-02 | 3 | bar: December/January/February 27 to December/January/February 28
9 | Development Start | 2025-12-02 | bar: December/January/February 29 to December/January/February 31